## Actions
ATC Committee | Cllr lead | Sub Area | Plan # | ATC # | Status | Town Plan Action | <6 mth | 6 – 18 mth | >18 mth | No | ATC Ctrl | SCDC Ctrl | SCC Ctrl | Other Org | Notes | NP | Status |  | Funding
Services |  | Town & Beach | 6 |  | 0 | (6) Consider a plan for the town as a whole to maintain and improve vistas while removing unnecessary street signage and clutter |  |  | Y |  | Y |  | y | Aldeburgh Society | Aldeburgh Society undertaking review for input into NP. The output can be actioned as part of the Town plan. | Y | Started |  | >£10k
Services | JB | Communications | 34 |  | 0 | (34) Undertake an “education” drive to show people how local government works and what is being achieved. |  | Y |  |  | Y |  |  |  | Website the main vehicle which is currently being improved and updated. Options could include articles in local publications. Ensure website to include the responsibilities of the 3 levels of Council. | N | Started |  | >£0k
Services |  | Communications | 36 |  | 0 | (36) Explore and develop the use of email and social media in contacting and consulting residents. |  |  | Y |  | Y |  |  |  | Could form part of long term Communication Strategy. No resource currently available to progress. Not seen as a high priority.Considered most suited for Emergency plan communications. Ensure reference to the website is included in all communications. | N | Not Started |  | >£10k
Services | JD | Communications | 37 |  | 0 | (37) Plan to hold more consulation meetings in the manner of the Town Plan preparations to gather responses and discuss issues directly. | Y |  |  |  | Y |  |  |  | Part of Communications Strategy. Need to be careful not to overload consultations with NP and River defence public meetings taking place. Meeting to be held on a Saturday morning in Sept 2017 at the Community Centre | N | Not Started |  | >£0k
Completed
Not Started
Services |  | Parking & Transport | 29 |  | 0 | (29) Enter negotiations with SCDC regarding the feasibility of taking over responsibility for operating the off-street car parks, for determining all parking charges, and for enforcement of parking controls. |  |  | Y |  | Y | Y | Y |  | Dependent upon the outcome of the Police review and their negotiations with SCDC regarding management of traffic/ parking. 13/2 SCDC confirmed they have agreed to take over parking enforcement although the details have yet to be agreed. Likely to take circa 24 mths. | The NP could include policies to address parking although would'nt cover operational issues such as parking charges. | Not started |  | >£10k
Services | SF | Parking & Transport | 30 | 2 | 0 | (30) Prepare a series of proposals for the development of parking schemes in line with the outcomes of the public consultation meetings and the questionnaires to include: Provision of free disabled parking bays outside the Chemist, Changes to the charges in the large car parks to provide free or very cheap parking for up to 2 hrs and scaled charges for longer periods, Reservation of spaces at Fort Green for free or very cheap all-day parking for duly accredited High St staff, to be administered in conjunction with the Aldeburgh Business Association, Further consideration of the practicalities of introducing a Residents' parking Scheme in the Terrace/Lee Rd. |  |  | Y |  | Y |  | Y |  | The reduced charges done. ATC to talk to ABA & to SCDC about the remainder. These will also be dependent to some extent on the police review as enforcement is a vital consideration. 13/2 Cllr Smith Confirmed the Rights of way committee will meet early March to review the 40mph restriction on Leiston road and the double yellow lines proposal for the Church farm road junction with Thorpe road to Church Rise. | The NP could include policies to address parking although would'nt cover operational issues such as parking charges and would need to focus on the land use aspects of parking. See saved policies AP128 and AP129. | Started |  | >£10k
Services | JD | Community & Road Safety | 23 |  | 0 | (23) A consultation to be undertaken with residents regarding the extension of the No Cold Calling Zone. |  |  | Y |  | Y |  |  | Police | Lack of PCSO presence will impact the ability to implement this. There would appear to be little demand. To test this assumption include as a question on the Website. Also to be included as an Agenda item for the Sept 2017 Town meeting to establish public requirement. | N | Not Started |  | >£0k
[17 empty] | Not Started | X
Underway
Services |  | Community & Road Safety | 26 |  | 0 | (26) Look at road safety, including the feasibility of introducing a school crossing patrol at the zebra crossing in Saxmundham Road. |  |  | Y |  | Y | Y | Y | School | Hi Vis tops provided for children walking to school. Improvements already made by school at school entrance. School do not support need for school crossing patrol.Areas where speed signs, such as the one on Sax Rd, would be effective being identified and ATC to budget to install one each year. | N | Not Started |  | >£10k
Services | JB | Community & Road Safety | 28 |  | 0 | (28) Review potential for changes to speed limits on Leiston Road and the town area east of the roundabout, conveying the wishes of the residents of the Town to the relevant authority. |  | Y |  |  | Y |  | Y |  | Cllr Smith progressing with Highways. As per (30) above and 13/2 he confirmed the Rights of Way committee will meet early March to review this speed limit proposal. | Y | Started |  | >£10k
Services |  | Museum & Heritage Area | 4 | 1 | #REF! | (4) Develop specific proposals and undertake a consultation with the town on the Museum and new conservation area topics. |  |  | Y | X | Y |  |  |  | Museum HLF successful bid will progress this in Partnership with Council. | Only if a new museum building could be shown to be deliverable (site identified etc). Conservation area could be included - see Saved policy AP1. | Started |  | >£10k
Services | MF | Museum & Heritage Area | 5 |  | 0 | (5) Improve interpretation of the different aspects and periods of the Town's Heritage (and environment) so that they are better understood, enjoyed and appreciated. |  |  | Y |  | Y |  |  | Aldeburgh Society, History Soc, Town Guide | As above. In addition a priority is to get the North lookout registered as a Community Asset. | If land use implications were identified this could be incorporated into a wider heritage policy. | Started |  | >£10k
Services |  | Arts Venues | 39 |  | 0 | (39) Form a partnership group to formulate proposals for: What's On website for the Town. Other shared services such as ticketing. 'Greater Aldeburgh' inclusion and co-operation. Support of : working with Schools and establishing other outreach; events in the Town; public consultation on refurbishment of venues in the Town; the establishment of a creative arts space. |  |  | Y |  | N |  |  | Aldeburgh Arts Partnership | Regular Arts partnership meetings held to share info. Now put on hold - risk that groups will go back into their silo's. Aldeburgh Living launched a weekly whats on ( currently on hold but to relaunch June/ July) and in March 2017 a quarterly magazine was published and second edition due for publication in June. | Only if proposals result in land use implications. | Started |  | >£0k
Governance |  | Health and voluntary | 10 |  | 0 | (10) Raise awareness of the Parish Nurse more widely. |  | Y |  |  | N |  |  | AUC and Patients Forum |  |  |  | X
Governance |  | Health and voluntary | 11 |  | 0 | (11) Increase the number of drivers for transporting patients to and from Ipswich and other specialist hospitals. |  | Y |  |  | N |  |  | AGNES |  |  |  | X
Governance |  | Health and voluntary | 12 |  | 0 | (12) Advertise community health services including those that support mental health. |  | Y |  |  | N |  |  | Patients Forum |  |  |  | X
Governance |  | Health and voluntary | 13 |  | 0 | (13) Request and encourage East Suffolk Clinical Commissioning Group to produce a directory of health services and a “how to” guide. |  | Y |  |  | N |  |  | Patients Forum | Underway |  |  | X
Governance |  | Health and voluntary | 14 |  | 0 | (14) Investigate the feasibility of introducing GP weekend and telephone appointments. |  | Y |  |  | N |  |  | Patients Forum |  |  |  | X
Governance |  | Health and voluntary | 15 |  | 0 | (15) Explore scope for a minor injuries clinic in the locality. |  | Y |  |  | N |  |  | Patients Forum |  |  |  | X
Services | JD | Town Guide | 40 |  | 0 | (40) Write a Town Guide for visitors. |  | Y |  |  | N |  |  | Aldeburgh Arts Partnership | The Bookshop have not yet started a guide. ATC discussing a new guide with local publishers for publication for summer 2017 | N | Started |  | >£10k
Not Started
Property | SJ | Sports Plan | 18 | 13, 14, 15, 16, 17, 18, 20, 21 | 0 | (18) Continue to support the Sports Plan for Aldeburgh and its proposals for future development including: plans to encourage football, improve the drainage of Kings Field and build new changing rooms, examine potential to expand Yoga, Pilates and Zumba classes as well as cricket, encourage and retain Sports Week for children, encourage wider use by residents of the existing sailing and Golfing facilities. |  |  | Y |  | Y |  |  | Community Centre mgt | ATC progressing. Sports vision understood. The successful grant award from Sport England will enable progress to be made on improving drainage and re-introducing 2 pitches. Rugby hut refurbishment commenced and Phase 1 scheduled to complete May 17. Funding being sought for Phase 2 - the changing rooms facilities. | Yes if land use implications are identified.See policy SP16 of Local Plan. | Started |  | <£10k>£100k
Property | SJ | Community Centre | 17 |  | 0 | (17) Encourage the development and use of more facilities at the Community Centre. | Y |  |  |  | Y |  |  | Community Centre mgt | Rugby, Lunches, Centre Manager to promote venue all introduced. Improved bookings system being implemented. Phoenix club, NADFAS and History Society now considering meeting here. Working with High Tide festival to use as a venue. | Y | Started |  | >£0k
Property |  | Walking and Cycling incl Paths | 2 |  | 0 | (2) Look to extend foot and bicycle paths to Thorpeness, Leiston and explore the potential for creation of a cycle path to Snape. |  |  | Y |  | Y | Y |  | Thorpeness, Sandlings Cycle Group. | Funding and land ownership considerations. Not a current priority. The requirement was included in ATC's Sizewell response to Stage 2. | Y | Not Started |  | <£100k
Planning |  | Shared Space | 6 |  | l | see 1b - Vistas and clutter |  |  | Y |  | Y |  |  |  | Part of NP | Y
Planning |  | Shared Space | 27 |  | l | (27) Develop a plan for the enhancement of the High Street environment , in conjuction with relevant councils and stakeholders, for further public consultation. |  |  | Y |  | Y |  |  |  | NP Shared space | Y
Property |  | Walking and Cycling incl Paths | 19 |  | 0 | (19) Develop a cycling strategy in consultation with the Sandlings Cycling Campaign and Cycle Suffolk, to include: Cycle lanes on the main access roads, additional cycle parking racks, dedicated cycle routes to Thorpeness and Snape, Targeted information for cyclists, including recognition of the 'shared space' nature of most routes used by cyclists. |  |  | Y |  | Y |  |  | Sandlings Cycle etc | ATC has representation with Sandlings Cycling but no resource or funds to actively progress. River wall potential to be debated but high cost. | Need to talk to adjoining parishes to ensure a coordinated approach. | Not Started |  | <£100k
Property |  | Walking and Cycling incl Paths | 20 |  | 0 | (20) Every encouragement to be given to cycle hire and maintenance in town, supported by 31% of visitors. |  |  | Y |  | Y |  |  | ATC to speak to DMO and ABA | Encouraging Farm shop site as suitable location. Local individual set up 'around' the town during the 2016 summer. Not a current priority. | Could be an aspect of a broader cycling policy although the plan cannot control the occupiers of commercial facilities. | Not Started |  | >£0k
Property |  | Walking and Cycling incl Paths | 32 |  | 0 | (32) Pursue the following lines of action in collaboration with local business interests, SCC, SCDC, the AONB and other partners: Review visitors' walking experiences within and around the town, including existing signage and routes from public car parks, especially Fort Green. Develop signage in the approach to the Town, to reveal and celebrate Aldeburgh's features. Undertake measures to establish the old railway line as a public right of way. Undertake measures to improve safe access to the start of the Sailors' Path. Develop a walkers' guide for the Town. |  |  | Y |  | Y |  |  |  | This could be partly covered in the Aldeburgh Society review. The railway line is privately owned and permission is currently granted by the owners for access. Funding issues a major consideration. . | Y. Also see policy AP30 | Not Started |  | <£10k>£100k
Planning |  | River and Sea Defences | 8 | 7 | 0 | (8) Adopt an information and engagement strategy for our whole community, to ensure people are well briefed about the Flood Defense and Coastal Management options. | Y |  |  |  | Y |  |  | Alde & Ore Partnership | Alde & Ore presentations to the public in Nov/Dec 2015. Further presentation held in Snape in June 2016 and demand would indicate one is needed in Aldeburgh to brief residents. Significant funding issues need to be understood.Presentation from A&OEP re funding options etc made to Council in Nov 2016 and to the public in March 2017. | N | Started |  | >£0k
Planning | PP | River and Sea Defences | 9 | 5 | 0 | (9) Draft issue and Publicise the Emergency Plan more widely | Y |  |  |  | Y |  |  |  | Updated and should be published shortly. JEPU needs updating. | N | Started |  | >£10k
Planning |  | Neighbourhood Plan | 16 |  | 0 | (16) Produce a Neighbourhood plan for Aldeburgh in 2015 including the preparation of a series of options to addess the provision for affordable housing, sheltered housing, starter homes, and the encouragement of permanent residence. |  | y |  |  | Y | Y |  |  | Resolution Feb 2017 to suspend activity following SAASP adoption and a review of latest information. Agreed to periodically review the decision depending on changes in information. | Y. The plan may not be able to address the issue of second homes ! | On hold |  | <£10k>£100k
Planning |  | Affordable Housing | 16 |  | 0 | see above on affordable housing |  | Y |  |  | Y |  | Y |  | Brickdock properties allocated with one under shared ownership. Awaiting completion of sale of Police site to Flagship, which is dependent on the scheme viability. Meeting with Flagship held 27 Sept 2016. Proposed scheme consultation held with the public late 2016. Final scheme, including recreation area proposal reviewed at Planning and supported. Awaiting SCDC decision. | Y | Started |  | >£10k
[16 empty] | Y | Underway | X
Planning |  | Fort Green | 1 |  | 0 | (1) Achieve an agreed approach and plan for the Fort Green area, perhaps tied into solutions for parking, with an interesting approach to the Town Centre and beyond. |  |  | Y |  | Y | Y |  |  | The area is proposed to be included in the revised Conservation area. Need to consider funding implications before publishing a plan. Alde Society forming a view of options, not seen as a priority due to the significant funding implications. | Y | Not Started |  | <£10k>£100k
ACTIONS NOT BEING PROGRESSED
Services |  | Quality status | 38 |  | 0 | (38) Begin the process of seeking Quality Town Council designation. | Y |  |  |  | Y |  |  |  | No Benefit
Property |  | ATC Services scope | 21 |  | 0 | (21) Identify which, if any, public community services might be developed along the lines of the Aldeburgh Library Foundation. |  | Y |  |  | Y |  |  |  | As an when an opportunity arises it will be considered | Only if land use implications can be identified.
Services |  | Schools | 22 |  | 0 | (22) Representation made to ?SCC & Academy regarding the quality of local secondary education. |  |  | Y |  | Y |  |  | Primary School Govs, Alde Valley academy | Beyond ATC Remit | N
Services |  | Parking & Transport | 31 |  | 0 | (31) Set up a consultation meeting between regular bus users, the operators and SCC, to explore possible improvements to services and establish a regular dialogue for the future |  | Y |  |  | Y | Y |  |  | ATC will get involved if a situation arises. | N
Services |  | Community & Road Safety | 24 |  | 0 | (24) A campaign to recruit more coordinators for Neighbourhood Watch. |  | Y |  |  | N |  | Y |  | This should be a police initiative and ATC will be involved via our SNT rep. | N
Services |  | Town & Beach | 3 |  | 0 | (3) Encourage use of the beach for everyone especially addressing access for those less physically able. |  |  | Y |  | Y | Y |  |  | Possibly considered under shared space in NP. Limited opportunities. Disabled access near the Scallop already in place but little used. Need to investigate funding options to ensure viable. The concencus reached is that there is sufficient access in place and access will always be a difficulty on a shifting, shingle beach. | Depends if there were specific land use implications. Could be incorporated into a wider policy about the beach area and /or accessibility in the town
COMPLETED ACTIONS
Services |  | Community & Road Safety | 25 |  | 0 | (25) Representation to the Suffolk Police regarding provision of Police and PCSO time and in particular consideration for funding more hours. | Y |  |  |  | Y |  |  |  | Already Done regularly. No additional action
Services |  | Public Toilets | 7 | 10,11 | 0 | (7) Upgrade the Public toilets |  | Y |  |  | Y | Y |  |  | Completed.
Services |  | Council & Volunteer list | 33 |  | 0 | (33) Mayor/Town Clerk to hold an informal meeting for all those willing to stand for the Town Council. | Y |  |  |  | Y |  |  |  | Done.
Services | JD | Communications | 35 |  | 0 | (35) Update the Town website with relevant local news and consultation opportunities. | Y |  |  |  | Y |  |  |  | Website upgrade largely complete and now subject to regular updating. | N
ALDEBURGH TOWN COUNCIL PROJECTS
ATC Committee | Cllr lead | Sub Area |  |  |  | Project Description | <6 mth | 6 – 18 mth | >18 mth |  | ATC Ctrl | SCDC Ctrl | SCC Ctrl | Other Org | Notes |  | Status |  | Funding
Property | SJ | Property |  |  |  | Moot Hall repairs | Y | [7 empty] | RJ Hoggs to repair the South end of the building and renovate and repaint the sundial. Internal repair to strengthen beam and prevent further movement. Works started and will be complete May. |  | Started |  | <£10k>£100k
Property | SF | Property |  |  |  | New kitchen | Y | [7 empty] | Replace kitchen with commercial unit incorporating dishwasher, microwave. In progress should be complete before 21 May. |  | Started |  | >£10k
Property | SJ | Recreation |  |  |  | New drainage for Kings field |  | Y | [5 empty] | Sport England | Grant awarded for £82500 in Sept 2016. Primary and secondary drainage to be installed on the bottom pitch. Legal requirements with Marshall Hatchick. Turf Argonomist works confirmed. Awaiting Argonomist advice re timing. Agronomist about to go to tender. |  | Started |  | >£10k
Property | SJ | Recreation |  |  |  | Replace play equipment in enclosed area on Kings field. | Y | [7 empty] | All equipment to be replaced and relocated to allow expansion of the Rugby hut. Recycled plastic furniture to be used to enable easy cleaning and to prevent rot. SJ/ LH/SO met supplier 21/2. quote received. Investigating grant with SCDC and use of S106 funds. Approval given at Council to proposed scheme. Finalising grant application. |  | Started |  | <£10k>£100k
Property | MW | Recreation |  |  |  | BMX track on Kemps field. | [8 empty] | Investigating the options to create a BMX track on Kemps field. Awaiting options update. |  | Started |  | >£10k
Property | SJ | Health and safety |  |  |  | New Dog bins with bag dispensers | Y | [7 empty] | New bins with bag dispensers to be introduced on Jubilee walk and the seafront to see if it reduces dog fouling. Bins received and sites identified for installation. New bins to be installed on the railway track and the park road end of the marshes footpath. |  | Started |  | >£10k
Property | SJ | Property |  |  |  | Refurbishment of Groundsmans cottage | Y | [7 empty] | Building sub divided to create 2 units. Office and storage unit refurbished. New roof installed. Humidistat fitted to storage area. Rating office contacted to separate rates. Office unit handed over to museum. Workshop options being considered. |  | Started |  | <£10k>£100k
Property | SJ |  |  |  |  | External decoration of Groundsmans cottage and Pet Perfection | Y | [7 empty] | Invitation to tender issued and quotes received and approved at April Council. Additional work on brick pillar identified and emergency work approved April Council and work to commence week beg 16 May. |  | Started |  | >£10k
Property | SJ | Property |  |  |  | Allotments | Y | [7 empty] | Unused allotments to be cleared and weed killer sprayed. Secondary Ditch at bottom of allotments cleared week beg 28 March. |  | Started |  | >£10k
Property | SJ | Recreation |  |  |  | Tennis courts maintenance | Y | [7 empty] | Upper court to be resprayed where surface is damaged and contractor appointed. Work to be complete before 20/21 May tournamnet, weather permitting. Flood light problems to be resolved with supplier. Meters to be replaced before the autumn. |  | Started |  | >£10k
Property | SJ | Recreation |  |  |  | Fitness centre |  | Y | [6 empty] | Explore opportunities to provide a unit for a fitness centre close to Kings field and the Community centre. SJ/PP met with potential provider 17/2. Business case to be developed. |  | Started |  | <£10k>£100k
Property |  | Property |  |  |  | Explore options to create additional car parking to relieve congestion on Leiston/Saxmundham rds. |  | Y | [6 empty] | Explore options to provide additional car parking to relieve congestion on Leiston and Saxmundham rds and to establish demand. |  | Not Started |  | >£10k
Property | SJ | Recreation |  |  |  | Sports Week 7-11 August 2017 | Y | [7 empty] | Organise annual Sports week. Programme finalised. Teeshirts ordered. Started fund raising. |  | Started |  | >£10k
Services |  | Health |  |  |  | Defibrillators |  | Y | [5 empty] | Health advisors - Doctors Surgery or parish nurse ? | Investigate potential suitable locations ahead of British Heart foundation funding which will be available later in 2017. |  | Started |  | >£10k
Services |  | Disabled access |  |  |  | Disabled access in the High St |  |  | Y |  |  |  | Y |  | Investigate options to improve disabled access in the High St |  | Not Started |  | >£10k
Services |  | Refuse collection |  |  |  | Keeping the town clean and tidy | Y |  |  |  |  | Y |  |  | Managing the relationship with Norse to ensure the town has the right service provision to keep the town clean and tidy. Discussing suitable bins for the Thorpe road car park. |  | Started |  | >£0k
Services |  | Road safety |  |  |  | Access roads speed limits |  |  | Y |  |  |  | Y |  | Leiston and Saxmundham road speed limits to ensure road safety. |  | Started |  | >£10k
Services |  | Transport |  |  |  | Leiston/Aldeburgh transport provision |  | Y |  |  | Y |  |  |  | With the ABA explore options to provide a regular service to principally support workers in the Town. |  | Not Started |  | >£10k
Planning |  | Planning |  |  |  | SAASP and Core Strategy |  |  | Y |  |  | Y |  |  | Ongoing support and input to the the development of these policies for Aldeburgh |  | Started |  | >£0k
Planning |  | Planning |  |  |  | Flood resiient housing |  |  | Y |  |  | Y |  |  | To understand the degree to which this is a planning consideration and to promote greater understanding and introduction as part of building regs. |  | Not Started |  | >£0k
Planning |  | Planning |  |  |  | Green Energy and insulation |  |  | Y |  |  | Y |  |  | Promote and investigate opportunities |  | Not started |  | >£10k
Planning |  | Planning |  |  |  | Existing and Off street parking |  |  | Y |  |  | Y |  |  | Vigilant approach to the retention of existing parking provisions in planning application reviews. |  | Started |  | >£0k
Planning |  | Planning |  |  |  | Conservation area extension |  |  | Y |  |  | Y |  |  | Project has started in unison with the Alde Soc and the conservation officer. Need to chase Robert Scrimgeor for his progress report. |  | Started |  | >£0k
Events |  | Community |  |  |  | Fireworks 5 November |  | Y | [6 empty] | Organise Fireworks event, including raffle. Kimbolton booked and Community Centre advised. |  | Started |  | >£10k
Completed
Planning |  | Planning |  |  |  | Brickdocks Objection | [8 empty] | Application refused
Planning |  | Planning |  |  |  | Sizewell Stage 2 response | [8 empty] | Response submitted
Services | JD | Car parking |  |  |  | Resurfacing of Thorpe Rd Car Park | Y | [7 empty] | New drainage and resurfacing of Thorpe Road car park
2017-05-01
Note on H67: Sally:

## Delivery Time
Aldeburgh Town Council |  |  |  |  | Town Plan Action items
Already Underway or completed (14) |  | TP # | ATC # | Status | Action | Notes
|  | 38 | 0 | 0 | (38) Begin the process of seeking Quality Town Council designation. | No Benefit
|  | 34 | 0 | 0 | (34) Undertake an “education” drive to show people how local government works and what is being achieved. | Website the main vehicle which is currently being improved and updated. Options could include articles in local publications. Ensure website to include the responsibilities of the 3 levels of Council.
|  | 30 |  | 0 | (30) Prepare a series of proposals for the development of parking schemes in line with the outcomes of the public consultation meetings and the questionnaires to include: Provision of free disabled parking bays outside the Chemist, Changes to the charges in the large car parks to provide free or very cheap parking for up to 2 hrs and scaled charges for longer periods, Reservation of spaces at Fort Green for free or very cheap all-day parking for duly accredited High St staff, to be administered in conjunction with the Aldeburgh Business Association, Further consideration of the practicalities of introducing a Residents' parking Scheme in the Terrace/Lee Rd. | The reduced charges done. ATC to talk to ABA & to SCDC about the remainder. These will also be dependent to some extent on the police review as enforcement is a vital consideration. 13/2 Cllr Smith Confirmed the Rights of way committee will meet early March to review the 40mph restriction on Leiston road and the double yellow lines proposal for the Church farm road junction with Thorpe road to Church Rise.
|  | 23 | 0 | 0 | (23) A consultation to be undertaken with residents regarding the extension of the No Cold Calling Zone. | Lack of PCSO presence will impact the ability to implement this. There would appear to be little demand. To test this assumption include as a question on the Website. Also to be included as an Agenda item for the Sept 2017 Town meeting to establish public requirement.
|  | 25 | 0 | l | (25) Representation to the Suffolk Police regarding provision of Police and PCSO time and in particular consideration for funding more hours. | Already Done regularly. No additional action
|  | 4 |  | 0 | (4) Develop specific proposals and undertake a consultation with the town on the Museum and new conservation area topics. | Museum HLF successful bid will progress this in Partnership with Council.
|  | 39 | NP? | l | (39) Form a partnership group to formulate proposals for: What's On website for the Town. Other shared services such as ticketing. 'Greater Aldeburgh' inclusion and co-operation. Support of : working with Schools and establishing other outreach; events in the Town; public consultation on refurbishment of venues in the Town; the establishment of a creative arts space. | Regular Arts partnership meetings held to share info. Now put on hold - risk that groups will go back into their silo's. Aldeburgh Living launched a weekly whats on ( currently on hold but to relaunch June/ July) and in March 2017 a quarterly magazine was published and second edition due for publication in June.
|  | 21 | NP | l | Affordable Housing | As an when an opportunity arises it will be considered
|  | 18 | NP | l | (18) Continue to support the Sports Plan for Aldeburgh and its proposals for future development including: plans to encourage football, improve the drainage of Kings Field and build new changing rooms, examine potential to expand Yoga, Pilates and Zumba classes as well as cricket, encourage and retain Sports Week for children, encourage wider use by residents of the existing sailing and Golfing facilities. | ATC progressing. Sports vision understood. The successful grant award from Sport England will enable progress to be made on improving drainage and re-introducing 2 pitches. Rugby hut refurbishment commenced and Phase 1 scheduled to complete May 17. Funding being sought for Phase 2 - the changing rooms facilities.
|  | 9 | 5 | l | (9) Draft issue and Publicise the Emergency Plan more widely | Updated and should be published shortly. JEPU needs updating.
|  | 16 |  | l | (16) Produce a Neighbourhood plan for Aldeburgh in 2015 including the preparation of a series of options to addess the provision for affordable housing, sheltered housing, starter homes, and the encouragement of permanent residence. | Resolution Feb 2017 to suspend activity following SAASP adoption and a review of latest information. Agreed to periodically review the decision depending on changes in information.
| Not ATC | 32 |  | l | (32) Pursue the following lines of action in collaboration with local business interests, SCC, SCDC, the AONB and other partners: Review visitors' walking experiences within and around the town, including existing signage and routes from public car parks, especially Fort Green. Develop signage in the approach to the Town, to reveal and celebrate Aldeburgh's features. Undertake measures to establish the old railway line as a public right of way. Undertake measures to improve safe access to the start of the Sailors' Path. Develop a walkers' guide for the Town. | This could be partly covered in the Aldeburgh Society review. The railway line is privately owned and permission is currently granted by the owners for access. Funding issues a major consideration. .
| Not ATC | 8 |  | l | (8) Adopt an information and engagement strategy for our whole community, to ensure people are well briefed about the Flood Defense and Coastal Management options. | Alde & Ore presentations to the public in Nov/Dec 2015. Further presentation held in Snape in June 2016 and demand would indicate one is needed in Aldeburgh to brief residents. Significant funding issues need to be understood.Presentation from A&OEP re funding options etc made to Council in Nov 2016 and to the public in March 2017.
|  | 40 |  | l | (40) Write a Town Guide for visitors. | The Bookshop have not yet started a guide. ATC discussing a new guide with local publishers for publication for summer 2017
Not Started - near & medium term (10) |  |  |  |  | NB 9 of the following 20 items might be best wrapped into the Neighbourhood Plan
|  | 36 |  | l | (36) Explore and develop the use of email and social media in contacting and consulting residents. | Could form part of long term Communication Strategy. No resource currently available to progress. Not seen as a high priority.Considered most suited for Emergency plan communications. Ensure reference to the website is included in all communications.
|  | 29 |  | l | (29) Enter negotiations with SCDC regarding the feasibility of taking over responsibility for operating the off-street car parks, for determining all parking charges, and for enforcement of parking controls. | Dependent upon the outcome of the Police review and their negotiations with SCDC regarding management of traffic/ parking. 13/2 SCDC confirmed they have agreed to take over parking enforcement although the details have yet to be agreed. Likely to take circa 24 mths.
|  | 35 |  | l | (35) Update the Town website with relevant local news and consultation opportunities. | Website upgrade largely complete and now subject to regular updating.
|  | 37 |  | l | (37) Plan to hold more consulation meetings in the manner of the Town Plan preparations to gather responses and discuss issues directly. | Part of Communications Strategy. Need to be careful not to overload consultations with NP and River defence public meetings taking place. Meeting to be held on a Saturday morning in Sept 2017 at the Community Centre
|  | 33 |  | l | (33) Mayor/Town Clerk to hold an informal meeting for all those willing to stand for the Town Council. | Done.
|  | 22 |  | l | (22) Representation made to ?SCC & Academy regarding the quality of local secondary education. | Beyond ATC Remit
|  | 24 |  | l | (24) A campaign to recruit more coordinators for Neighbourhood Watch. | This should be a police initiative and ATC will be involved via our SNT rep.
|  | 26 |  | l | (26) Look at road safety, including the feasibility of introducing a school crossing patrol at the zebra crossing in Saxmundham Road. | Hi Vis tops provided for children walking to school. Improvements already made by school at school entrance. School do not support need for school crossing patrol.Areas where speed signs, such as the one on Sax Rd, would be effective being identified and ATC to budget to install one each year.
| Not ATC | 28 |  | l | (28) Review potential for changes to speed limits on Leiston Road and the town area east of the roundabout, conveying the wishes of the residents of the Town to the relevant authority. | Cllr Smith progressing with Highways. As per (30) above and 13/2 he confirmed the Rights of Way committee will meet early March to review this speed limit proposal.
|  | 5 | NP | l | (5) Improve interpretation of the different aspects and periods of the Town's Heritage (and environment) so that they are better understood, enjoyed and appreciated. | As above. In addition a priority is to get the North lookout registered as a Community Asset.
Not Started - long term (10)
|  | 3 | NP | l | (3) Encourage use of the beach for everyone especially addressing access for those less physically able. | Possibly considered under shared space in NP. Limited opportunities. Disabled access near the Scallop already in place but little used. Need to investigate funding options to ensure viable. The concencus reached is that there is sufficient access in place and access will always be a difficulty on a shifting, shingle beach.
|  | 6 | NP | l | (6) Consider a plan for the town as a whole to maintain and improve vistas while removing unnecessary street signage and clutter | Aldeburgh Society undertaking review for input into NP. The output can be actioned as part of the Town plan.
|  | 31 |  | l | (31) Set up a consultation meeting between regular bus users, the operators and SCC, to explore possible improvements to services and establish a regular dialogue for the future | ATC will get involved if a situation arises.
|  | 7 | NP | l | (7) Upgrade the Public toilets | Completed.
|  | 17 | NP | l | (17) Encourage the development and use of more facilities at the Community Centre. | Rugby, Lunches, Centre Manager to promote venue all introduced. Improved bookings system being implemented. Phoenix club, NADFAS and History Society now considering meeting here. Working with High Tide festival to use as a venue.
|  | 20 | NP | l | (20) Every encouragement to be given to cycle hire and maintenance in town, supported by 31% of visitors. | Encouraging Farm shop site as suitable location. Local individual set up 'around' the town during the 2016 summer. Not a current priority.
|  | 16 | NP | l | see above on affordable housing | Brickdock properties allocated with one under shared ownership. Awaiting completion of sale of Police site to Flagship, which is dependent on the scheme viability. Meeting with Flagship held 27 Sept 2016. Proposed scheme consultation held with the public late 2016. Final scheme, including recreation area proposal reviewed at Planning and supported. Awaiting SCDC decision.
|  | 0 | NP | l | 0
|  | 1 |  | l | (1) Achieve an agreed approach and plan for the Fort Green area, perhaps tied into solutions for parking, with an interesting approach to the Town Centre and beyond. | The area is proposed to be included in the revised Conservation area. Need to consider funding implications before publishing a plan. Alde Society forming a view of options, not seen as a priority due to the significant funding implications.
|  | 0 | NP | l | 0 | 0
Health Items (6)
|  | 10 |  | l | (10) Raise awareness of the Parish Nurse more widely. | Not ATC directly - Patients forum
|  | 11 |  | l | (11) Increase the number of drivers for transporting patients to and from Ipswich and other specialist hospitals.
|  | 12 |  | l | (12) Advertise community health services including those that support mental health.
|  | 13 |  | l | (13) Request and encourage East Suffolk Clinical Commissioning Group to produce a directory of health services and a “how to” guide.
|  | 14 |  | l | (14) Investigate the feasibility of introducing GP weekend and telephone appointments.
|  | 15 |  | l | (15) Explore scope for a minor injuries clinic in the locality.

## Decision Tree
Decision Tree
TP Action
Understood?
Accepted
?
ATC Power
?
Committee sufficient ?
Assign Task to committee
Another Agency
?
NO
Evaluate with Partnership
NO
NO
NO
Agency sufficient ?
NO
NO
Publicise Rejection or Deferral
Assign to Partnership
ATC Committee assigned to monitor
Publicise Timeline
&
Publicise Delivery

## Summary
Town Plan Actions Summary: Status
Broad Area |  | ATC Responsibility | Town Plan Action Numbers | Status | New Status
Partnership group
1. Services |  | ATC Services
| a. Quality Status |  | 38 | l
| b. Communications | ?tbd | 34, 35, 36, 37 | l
| c. Council and volunteer list |  | 33 | 0
| d. Schools | SCC | 22 | l
| e. Parking & Transport | SCDC | 29, 30, 31 | l
| f. Public Toilets | SCDC | 7 | l
| g. Community & Road safety | SCDC | 23, 24, 25, 26, 28 | l
| h. Health and voluntary actions | Patients forum, AUC, AGNES | 10,11,12.13,14,15 | l
2. Town as Destination |  | ATC Services
| a. Town & Beach | SCDC | 3, 6 | l
| b. Museum & Heritage Area | Aldeburgh Arts | 4, 5 | l | v
| c. Arts Venues | Aldeburgh Arts | 39 | l
| d. Town Guide | Aldeburgh Arts | 40 | l
3. Planning |  | ATC Planning
| a. Neighbourhood plan | Aldeburgh Society | 16 | l
| b. Affordable Housing |  | 16 | l
| c. Conservation area | Aldeburgh Society | 4 | l
| d. Fort Green | Aldeburgh Society | 1 | l
| e. Follow up “Shared space” | Aldeburgh Society | 3, 6, 27 | l
| g. River and Sea defences | Alde & Ore | 8, 9 | l
4. Town Facilities & Finance |  | ATC Property & Finance
| a. Sports Plan | ?tbd | 18 | l
| b. Community Centre | CC trustees & mgt | 17 | l
| c. Walking & Cycling incl. Paths |  | 2, 19, 20, 32 | l
| d. ATC Services scope |  | 21 | l